## KA Schedule
SCHEDULE OF PROJECT KEY ACTIVITIES Innovation and Education for the Transformation of the Research Environment at IEB (INOVATE)
|  |  | Implementation period of the key activity. | [9 empty] | No public procurement procedures are planned under the INOVATE project
|  |  | Implementation period of the sub-activity | [9 empty] | Output
year | 2025 |  |  |  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
calendar month | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2
project month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
KA2: Strategic management of the research organisation in line with the requirements for obtaining the HR Award
KA2.1 Obtaining the HR Award | [8 empty] | GAP Analysis | Action Plan | HR Award application
KA2.2 Interim assessment of the RO with the EC and implementation of the revised Action Plan | [37 empty] | Revised Action Plan
KA2.3 Training and development of knowledge and skills |  |  | HRS4R training
KA3: Human resources development in line with the principles of the HR Award
KA3.1 Development/implementation of the Long-term Human Resources Management Development Strategy, pilot operation | [17 empty] | Strategy |  | Implemented Strategy | Updated GEP, guideline | Gender-sensitive guide | IEB Career Regulations
KA3.2 Establishment and pilot operation of the Project Office | Project Office established
KA3.3 Training and knowledge development | [9 empty] | Good practice |  | HR/recruitment training | Project training |  | Communication training |  |  | AI for research/admin/practice | [5 empty] | Energy Mgmt./Internship/practice | Project training |  |  |  |  | Mng emotions |  | Good practice |  |  |  | Work-life balance | AI for research/admin. staff/Project training |  |  | Good practice
KA4: Development of research organisation management
KA4.1 Development and subsequent implementation of the IEB Management Strategy | [12 empty] | Leadership training | [12 empty] | Strategy |  | Implemented Strategy | [11 empty] | Leadership training
KA4.2 Development of online OHS, first aid and fire safety tests | [10 empty] | Online tests | Training | [11 empty] | Training | [11 empty] | Training
KA5: Development of research organisation evaluation
KA5.2 Development/implementation of the IEB Evaluation Strategy | [8 empty] | Online appraisal form | Analytical report | [15 empty] | Strategy |  | Implemented Strategy
KA5.3 Evaluation of the administrative/technical team | [13 empty] | Report
KA5.4 Courses and training | [15 empty] | Self-assessment | [23 empty] | Self-assessment
KA6: Development of international R&D cooperation and internationalisation of the research organisation
KA6.1 Development and subsequent implementation of the IEB Internationalisation Strategy | [6 empty] | Report | [6 empty] | Strategy |  | Implemented Strategy
KA6.2 Pilot testing of the IEB Internationalisation Strategy | [15 empty] | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation |  | Seminar/Consultation/Report
KA6.3 Introduction of English as the organisation’s second working language | [5 empty] | EN | EN | EN | EN | EN |  |  | EN | EN | EN | EN | EN | EN | EN | EN | EN | EN |  |  | EN | EN | EN | EN | EN | EN | EN | EN | EN |  |  |  | EN | EN | Translations/EN | EN
KA6.4 Establishment of the Welcome Office, including pilot testing | Established | [6 empty] | Onboarding brochure
KA7: Development of intersectoral cooperation and technology transfer
KA7.1 Development and subsequent implementation of the Technology Transfer and Intersectoral Cooperation Strategy | [9 empty] | Report | [13 empty] | Strategy | Guidelines | Implemented Strategy
KA7.2 Establishment of the Technology Transfer Office, including pilot testing | TT Office established
KA7.3 Training | [9 empty] | Legislation and IP | [5 empty] | Good practice |  | IP management | [5 empty] | Good practice |  |  | IP workshop | IP at IEB/Conference | [7 empty] | Conference | IP management |  | IP workshop |  | Good-practice sharing
KA8: Strategic framework and development of Open Science at the research organisation
KA8.1 Development and subsequent implementation of the Open Science Guidelines | [7 empty] | Report | [15 empty] | Guidelines |  | Implemented guidelines |  | DMP template
KA8.2 Training | OS Fair |  | OS training | [9 empty] | Academic writing |  |  | Data management/Good practice | [7 empty] | Good practice | Academic writing | OS training |  | Data management | [8 empty] | Academic writing | OS training |  | Data management
KA9: Establishment of a system to strengthen institutional resilience against illegitimate influence
KA9.1 Development and subsequent implementation of the IEB Resilience Strategy | [6 empty] | Report | [10 empty] | Strategy | Counter-influence manual | Implemented Strategy
KA9.2 Introduction of a due diligence specialist position and pilot testing of the IEB Resilience Strategy | DD specialist | [40 empty] | Pilot operation report
KA9.3 Training |  | Due diligence | [9 empty] | IR training/IR in IT |  |  |  | Internal IR training | [7 empty] | IR in IT | [6 empty] | Due diligence |  |  |  |  | IR training/IR in IT |  |  |  | Internal IR training
KA10: Support for the popularisation of R&D, including communication and marketing
KA10.1 Development, subsequent implementation and pilot testing of the IEB Communication Strategy |  |  | Media plan |  |  |  |  | Report |  |  | Annual report |  |  |  | Media plan | Summer school |  | Strategy |  | Implemented Strategy |  |  | Annual report |  |  |  | Media plan | Summer school | [5 empty] | Annual report |  |  |  |  | Media plan | Summer school |  | Summer school report/Photos
KA10.2 Establishment of the Communication and PR Office, including pilot testing | Office established
KA10.3 Training | [11 empty] | Science communication training | Social media training | [6 empty] | Graphic design training |  |  |  | Social media training |  | Copywriting training | [9 empty] | Social media training |  |  |  | Leisure-time educator course